## First pass
Brief sentence to describe the risk | Initial Probability | Impact | Initial risk level | Response | risk trend | last update
first risk, it to deploy the sheeet with bug included | Low | Moderate | low | Tolerate | Stable | 3 nov 20225
second risk, no clear explanation available | Low | Moderate | low | Tolerate | Stable | 3 nov 20225
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description
risk description

## H&M risks
|  |  | risk trend |  | Last update |  | Initial risk level | final risk level
One brief sentence to identify the risk |  |  | Stable |  |  |  | high | low
Description |  | Creation date | Disposition |  |  |  |  | Disposition date
Risk description or Issue description - Cause/Impact |  |  | Response | Rational of the disposition |  |  |  | Decision maker
Avoid
Initial Probability | High | Mitigation plan |  |  |  | Status | Final Probability | Low
Probability | 41 ~ 60% |  |  |  |  | Project execution plan adapted accordingly | Probability | 11 ~ 20%
Initial impact | High | [5 empty] | Final impact | Moderate
Project cost | US$ 101K - 200K | [5 empty] | Project cost | US$ 51K - 100K
Delay | 21 ~ 40 days | [5 empty] | Delay | 11 ~ 20 days
Scope | Major slip in key requirements | [5 empty] | Scope | Moderate slip in key requirement
Contingency Plan (immediate response and fall back plan) |  |  | Cost (k.euros) - to be included in the program | delay induced by risk (days)
Second risk in your database, use the "+" to expand |  |  | Stable |  |  |  | medium | medium
Description |  | Creation date | Disposition |  |  |  |  | Disposition date
Risk description or Issue description - Cause/Impact |  |  | Response | Rational of the disposition |  |  |  | Decision maker
Initial Probability | High | Mitigation plan |  |  |  | Status | Final Probability | High
Probability | 41 ~ 60% |  |  |  |  | Project execution plan adapted accordingly | Probability | 41 ~ 60%
Initial impact | Moderate | [5 empty] | Final impact | Moderate
Project cost | US$ 51K - 100K | [5 empty] | Project cost | US$ 51K - 100K
Delay | 11 ~ 20 days | [5 empty] | Delay | 11 ~ 20 days
Scope | Moderate slip in key requirement | [5 empty] | Scope | Moderate slip in key requirement
Contingency Plan (immediate response and fall back plan) |  |  | Cost (k.euros) - to be included in the program | delay induced by risk (days)
Third risk in your database, copy paste the block to create a new one |  |  | Stable |  |  |  | medium | medium
Description |  | Creation date | Disposition |  |  |  |  | Disposition date
Risk description or Issue description - Cause/Impact |  |  | Response | Rational of the disposition |  |  |  | Decision maker
Initial Probability | Very high | Mitigation plan |  |  |  | Status | Final Probability | High
Probability | 61 ~ 99% |  |  |  |  | Project execution plan adapted accordingly | Probability | 41 ~ 60%
Initial impact | Low | [5 empty] | Final impact | Moderate
Project cost | US$ 11K - 50K | [5 empty] | Project cost | US$ 51K - 100K
Delay | 6 ~ 10 days | [5 empty] | Delay | 11 ~ 20 days
Scope | Minor slip in requirement | [5 empty] | Scope | Moderate slip in key requirement
Contingency Plan (immediate response and fall back plan) |  |  | Cost (k.euros) - to be included in the program | delay induced by risk (days)

## Legends
Risk Analysis - legends
table of value associated to risk levels
| Rank | Probability | Impact
| Very high | 10 | 10
| High | 7 | 7
| Moderate | 5 | 5
| Low | 3 | 3
| Very low | 1 | 1
Risk level : visual
| RISK |  | Impact
|  |  | Very low | Low | Moderate | High | Very high
| Probability | Very high | Low | Medium | High | High | High
|  | High | Low | Medium | Medium | High | High
|  | Moderate | Low | Low | Medium | Medium | High
|  | Low | Low | Low | Low | Medium | Medium
|  | Very low | Low | Low | Low | Low | Low
Legend :
| Low | Monitoring only
| Medium | Establish risk response plan
| High | Establish risk response plan & implement strategy
To be adjusted to your project
Probability & Impact scale
|  |  | for contingency |  | Impact
| Scale | Probability | Probability | Scale | Project cost |  | Schedule | Scope | Quality
| Very high | 61 ~ 99% | 99% | Very high | > US$200K |  | > 40 days | Cannot achieve major program requirement | Very significant impact on overall functionality
| High | 41 ~ 60% | 60% | High | US$ 101K - 200K |  | 21 ~ 40 days | Major slip in key requirements | Significant impact on overall functionality
| Moderate | 21 ~ 40% | 40% | Moderate | US$ 51K - 100K |  | 11 ~ 20 days | Moderate slip in key requirement | Some impact in key functional areas
| Low | 11 ~ 20% | 20% | Low | US$ 11K - 50K |  | 6 ~ 10 days | Minor slip in requirement | Minor impact on overall functionality
| Very low | 1 ~ 10% | 10% | Very low | < US$ 10K |  | 1 ~ 5 days | Minimal or no impact | Minor impact on secondary functions
PMI book The Standard for Risk management : 2019 page 136 figure X6-9
Risk response (list & definition)
| Technique | Description
| Avoid | Make changes on the project to avoid completely
| Transfer | Transfer to High & Medium risk DB
| Mitigate | Taking action to reduce the probability and/or impact of the risk
| Tolerate | Decision not to make changes on the project to avoid risk
Risk trends (list & definition)
| Technique | Description
| Materialized | Risk is materialized and team has to deal twith the situation
Stable
| Increase | external conditions or inefficient mitigation plan
| decrease | External conditions improve or mitigation plan progress well
Status mitigation plan (list & definition)
| Status |  |  | Description
| creation |  |  | mitigation plan defined
| Project execution plan adapted accordingly |  |  | global project plan have now the risk mitigation items included in the overall execution
| execution under control |  |  | items of mitigation plan are on schedule and quality
| execution completed |  |  | mitigation plan is succesfuly completed